## Slide 1
ILLUSTRATIVE SCENARIO
October shipments need a decision
Constructed manufacturer, $200m annual revenue. As of September 25, 2026.
$250,000
EXPEDITE EXPENSE CAP
Approval needed by September 28.
RELEASE CONDITIONS
Written supplier allocation
and a feasible production schedule.
OWNER COO
Management limit: $100,000 in this example.
BOARD APPROVAL
Pending
KENNEDY RISK GROUP / EXECUTIVE RISK REPORT / 01
Notes: Purpose: identify the single decision or oversight question before showing detail. Keep proposals, approvals and implementation distinct. If no approval is needed, identify the assumption directors should challenge. Example: $250,000 is incremental expense, not total order value or working capital. Management delegation of $100,000 is invented for the example and is not a recommended policy. Spending must not start merely because the request appears in the deck.
Original Kennedy Risk Group template, version 2.0, September 25, 2026. All example companies, amounts, roles, dates, thresholds and evidence are constructed. No KRG client engagement is represented. The slides support discussion, not an assurance or compliance conclusion. Adapt governance and authority to the organization. Reference: https://kennedyriskgroup.com/blog/board-ready-risk-reporting . The Agenda Test: what changed, what could break the plan, what needs a decision. KRG Risk Chain: trigger, transmission, constraint, financial outcome. Use the blank deck for your own data. Delete bracketed prompts and retain material limitations. Do not imply a proposed action has already reduced exposure.

## Slide 2
ILLUSTRATIVE SCENARIO
Enterprise risk overview
Selected risks for this illustrative reporting cycle. The full register remains in the pre-read.
KENNEDY RISK GROUP / EXECUTIVE RISK REPORT / 02
Risk / direction | Objective affected | Evidence and next step
R-01 Supply Worsening | October shipments | COO: $12m of orders exposed. Approval request on slide 1. Allocation unconfirmed.
R-02 System recovery Uncertain | Reliable operations | CIO: recovery evidence is stale. Retest before changing the assessment.
R-03 Finance coverage Stable | Timely financial close | CFO: backup coverage is in place. Reassess if the trained backup is unavailable.
Stable is not low risk. Uncertain means the evidence is insufficient.
Notes: Purpose: preserve an enterprise view before the decision deep dive. This is a selected portfolio, not the full register or an assurance opinion. The additional R-02 and R-03 examples are constructed and deliberately qualitative because no exposure estimate is supplied. Direction and magnitude are separate. Do not interpret stable as safe, or missing evidence as low risk. Replace role titles with accountable names, add source dates and show the approved boundaries in the company version.
Original Kennedy Risk Group template, version 2.0, September 25, 2026. All example companies, amounts, roles, dates, thresholds and evidence are constructed. No KRG client engagement is represented. The slides support discussion, not an assurance or compliance conclusion. Adapt governance and authority to the organization. Reference: https://kennedyriskgroup.com/blog/board-ready-risk-reporting . The Agenda Test: what changed, what could break the plan, what needs a decision. KRG Risk Chain: trigger, transmission, constraint, financial outcome. Use the blank deck for your own data. Delete bracketed prompts and retain material limitations. Do not imply a proposed action has already reduced exposure.

## Slide 3
ILLUSTRATIVE SCENARIO
Trace the delay into the operating plan
R-01 / October shipments. KRG Risk Chain: trigger, transmission, constraint, financial outcome.
KENNEDY RISK GROUP / EXECUTIVE RISK REPORT / 03
TRIGGER
Four-week supplier delay
TRANSMISSION
Assembly interrupted; October shipments late
CONSTRAINT
No substitute qualified before October
FINANCIAL OUTCOME
$3.6m October contribution at risk
THE ASSUMPTION THAT CHANGED
Previous plan: delivery supported October shipments. Now: $12m of orders exposed; an $8m recovery allocation remains unconfirmed.
Confidence: medium. Written supplier confirmation is still pending.
Notes: Purpose: separate a changed fact from a changed opinion. Include source and as-of date for each material fact in the actual company version. If a number changed because methodology changed, say so. The illustrative supplier notice, order book and allocation are constructed evidence, not documents held by KRG. Operations expects recovery while Finance requires written confirmation. Keep that disagreement visible until resolved.
Original Kennedy Risk Group template, version 2.0, September 25, 2026. All example companies, amounts, roles, dates, thresholds and evidence are constructed. No KRG client engagement is represented. The slides support discussion, not an assurance or compliance conclusion. Adapt governance and authority to the organization. Reference: https://kennedyriskgroup.com/blog/board-ready-risk-reporting . The Agenda Test: what changed, what could break the plan, what needs a decision. KRG Risk Chain: trigger, transmission, constraint, financial outcome. Use the blank deck for your own data. Delete bracketed prompts and retain material limitations. Do not imply a proposed action has already reduced exposure.

## Slide 4
ILLUSTRATIVE SCENARIO
How much October contribution is exposed?
Conditional scenario, $ million. Contribution exposure excludes the separate response expense.
KENNEDY RISK GROUP / EXECUTIVE RISK REPORT / 04
Chart: 
| If $8m ships on time | Before response
October contribution at risk | 1.2 | 3.6
$12m × 30% = $3.6m | ($12m − $8m) × 30% = $1.2m
Separate expedite expense: up to $250,000.
Timing may shift contribution between periods. These are not expected losses.
Notes: Check arithmetic: 12.0 x 0.30 = 3.6; (12.0 - 8.0) x 0.30 = 1.2. The $0.25m expense is separate. No probabilities are specified, so do not present the amounts as expected loss, ROI, realized savings or proved risk reduction. Confirm the contribution definition, cancellations, cost behavior and cash timing with Finance. KRG Risk Chain in this example: trigger is a four-week supplier delay; transmission is interrupted assembly and late shipment; constraint is no substitute qualification before October; financial outcome is contribution at risk in October. In a real deck, show uncertainty ranges where supported.
Original Kennedy Risk Group template, version 2.0, September 25, 2026. All example companies, amounts, roles, dates, thresholds and evidence are constructed. No KRG client engagement is represented. The slides support discussion, not an assurance or compliance conclusion. Adapt governance and authority to the organization. Reference: https://kennedyriskgroup.com/blog/board-ready-risk-reporting . The Agenda Test: what changed, what could break the plan, what needs a decision. KRG Risk Chain: trigger, transmission, constraint, financial outcome. Use the blank deck for your own data. Delete bracketed prompts and retain material limitations. Do not imply a proposed action has already reduced exposure.

## Slide 5
ILLUSTRATIVE SCENARIO
Expediting has a condition attached
Recommendation: approve a capped response only when the delivery conditions are met.
KENNEDY RISK GROUP / EXECUTIVE RISK REPORT / 05
Option | Incremental expense | Tradeoff
Keep the current plan | No expedite spend. | Up to $3.6m October contribution at risk in this scenario.
Expedite allocation | Up to $0.25m. | Potentially $1.2m remains at risk, excluding response cost. Supplier confirmation needed.
Qualify a substitute | Not yet estimated. | Cannot protect October. Scope and cost needed for a later decision.
Release funds only when both conditions hold. If either fails, management returns with a revised choice.
Notes: Purpose: make the actual tradeoff clear. Do not manufacture a numeric estimate for an unpriced alternative. State the cost basis and time period consistently. Show management recommendations separately from the board decision. Example authority is constructed: the $250,000 request exceeds the $100,000 management limit. Ask for approval of the cap and conditions, not permission to assume the recovery will happen.
Original Kennedy Risk Group template, version 2.0, September 25, 2026. All example companies, amounts, roles, dates, thresholds and evidence are constructed. No KRG client engagement is represented. The slides support discussion, not an assurance or compliance conclusion. Adapt governance and authority to the organization. Reference: https://kennedyriskgroup.com/blog/board-ready-risk-reporting . The Agenda Test: what changed, what could break the plan, what needs a decision. KRG Risk Chain: trigger, transmission, constraint, financial outcome. Use the blank deck for your own data. Delete bracketed prompts and retain material limitations. Do not imply a proposed action has already reduced exposure.

## Slide 6
ILLUSTRATIVE SCENARIO
Set the next decision before the next meeting
R-01 / Illustrative decision conditions, not company-wide risk appetite. Milestones are not to scale.
KENNEDY RISK GROUP / EXECUTIVE RISK REPORT / 06
SEP 25
Report as of date
SEP 28 / NOON CENTRAL
Written allocation due
SEP 28
Funding decision due
OCT 2
COO review
If this happens | Owner and required response
No allocation by Sep 28, noon Central. | Procurement informs COO and CFO before that day’s funding decision.
Response forecast exceeds $1.2m of October contribution at risk. | COO and CFO review. Notify board chair within one business day.
Proposed expense exceeds $250,000. | CFO seeks renewed approval before additional commitment.
Procurement checks daily. Escalate earlier whenever a trigger is met.
Notes: Make each trigger operational: metric, source, observation frequency, exact boundary, owner, recipient and response time. Use exceeds or at least deliberately. The boundaries on this slide are constructed proposal conditions. They are not established risk appetite and should not be copied as universal thresholds. Faster incident escalation may be required by the actual organization. A regular meeting does not replace event-triggered escalation.
Original Kennedy Risk Group template, version 2.0, September 25, 2026. All example companies, amounts, roles, dates, thresholds and evidence are constructed. No KRG client engagement is represented. The slides support discussion, not an assurance or compliance conclusion. Adapt governance and authority to the organization. Reference: https://kennedyriskgroup.com/blog/board-ready-risk-reporting . The Agenda Test: what changed, what could break the plan, what needs a decision. KRG Risk Chain: trigger, transmission, constraint, financial outcome. Use the blank deck for your own data. Delete bracketed prompts and retain material limitations. Do not imply a proposed action has already reduced exposure.

## Slide 7
ILLUSTRATIVE SCENARIO
Approval and recovery remain open
Working record as of September 25, 2026. All actions below are open or pending.
KENNEDY RISK GROUP / EXECUTIVE RISK REPORT / 07
Deliverable / evidence | Owner | Due / status
Written supplier allocation and order mapping. | Procurement Director | Sep 28 / Open
Margin, cash timing and expense-cap review. | CFO | Sep 28 / Open
Feasible production and freight schedule. | Operations Director | Sep 28 / Open
Approval record with conditions and limits. | Corporate Secretary | Sep 28 / Pending
Next review: October 2. Verify actual shipments before changing the exposure assessment.
Notes: Purpose: give directors a way to follow through on prior commitments. In the company version, name individuals rather than relying only on job titles. An action can be complete while the risk remains. Record evidence of actual effectiveness separately from task completion. Preserve material dissent. This working record supplements the organization's formal minutes and approved records; it does not replace them.
Original Kennedy Risk Group template, version 2.0, September 25, 2026. All example companies, amounts, roles, dates, thresholds and evidence are constructed. No KRG client engagement is represented. The slides support discussion, not an assurance or compliance conclusion. Adapt governance and authority to the organization. Reference: https://kennedyriskgroup.com/blog/board-ready-risk-reporting . The Agenda Test: what changed, what could break the plan, what needs a decision. KRG Risk Chain: trigger, transmission, constraint, financial outcome. Use the blank deck for your own data. Delete bracketed prompts and retain material limitations. Do not imply a proposed action has already reduced exposure.